## نظرة عامة
عنوان | القيمة
اسم المشروع | منصة مقود
نوع المشروع | منصة خدمات السيارات
مدة MVP | 12 Sprint ( أسبوع / 6 أشهر)
مدة كل Sprint | أسبوعين
Backend Developer .NET | 2
Frontend React Developer | 2
UI/UX Designer | 1
QA Tester | 1
DevOps / Backend Support | 1 (جزئي)
Project Manager / Tech Lead | 1
إجمالي الفريق | 8 أعضاء

## نطاق MVP
النوع | الميزة | الحالة
MVP | تسجيل العملاء ومقدمي الخدمة | Must Have
MVP | إدارة المركبات | Must Have
MVP | استعراض الخدمات ومقدمي الخدمة | Must Have
MVP | إنشاء طلب خدمة | Must Have
MVP | إرسال عروض أسعار من مقدمي الخدمة | Must Have
MVP | قبول العرض من العميل | Must Have
MVP | تتبع حالة الطلب | Must Have
MVP | الدفع الأساسي / المحفظة | Must Have
MVP | التقييم | Must Have
MVP | لوحة إدارة بسيطة | Must Have
MVP | إشعارات أساسية | Must Have
MVP | رفع صور ومستندات | Must Have
Later | الذكاء الاصطناعي لتقدير الحوادث | Later
Later | OCR لمستندات التأمين | Later
Later | مقارنة وشراء التأمين | Later
Later | المتجر الإلكتروني لقطع الغيار | Later
Later | نظام النزاعات المتقدم | Later
Later | تتبع السائق المباشر كل 5 ثوانٍ | Later
Later | Elasticsearch | Later
Later | تقارير مالية متقدمة | Later

## السبرنتات
Sprint | الهدف | الفئة | المهمة | الوصف
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Solution | إنشاء ASP.NET Core Web API Solution
Sprint 0 | التحضير والتحليل التقني | Backend | اختيار المعمارية | Clean Architecture: API, Application, Domain, Infrastructure
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد EF Core | ربط Server SQL + PostGIS إن توفر
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Authentication Structure | تجهيز JWT, Refresh Token, OTP structure
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Base Entities | BaseEntity, AuditableEntity, SoftDelete
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Result Pattern | Result<T>, ErrorResponse, Pagination
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Swagger | توثيق API
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Docker Compose | API + Sql Server + Redis + MinIO
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Logging | Serilog
Sprint 0 | التحضير والتحليل التقني | Backend | إعداد Global Exception Handler | معالجة موحدة للأخطاء
Sprint 0 | التحضير والتحليل التقني | Frontend | إنشاء React App | React + Vite + TypeScript
Sprint 0 | التحضير والتحليل التقني | Frontend | إعداد Routing | React Router
Sprint 0 | التحضير والتحليل التقني | Frontend | إعداد State Management | Zustand أو Redux Toolkit
Sprint 0 | التحضير والتحليل التقني | Frontend | إعداد API Client | Axios مع Interceptors
Sprint 0 | التحضير والتحليل التقني | Frontend | إعداد Auth Guard | Protected Routes
Sprint 0 | التحضير والتحليل التقني | Frontend | إعداد UI Library | Tailwind + shadcn/ui أو MUI
Sprint 0 | التحضير والتحليل التقني | Frontend | إعداد Folder Structure | modules-based structure
Sprint 0 | التحضير والتحليل التقني | UI/UX | تحليل المستخدمين | Customer, Provider, Driver, Admin
Sprint 0 | التحضير والتحليل التقني | UI/UX | إعداد Design System | Colors, Typography, Buttons, Inputs
Sprint 0 | التحضير والتحليل التقني | UI/UX | إعداد Wireframes أولية | Auth, Dashboard, Orders
Sprint 0 | التحضير والتحليل التقني | UI/UX | إعداد User Flow | Flow حجز خدمة، عرض سعر، قبول عرض
Sprint 1 | Authentication & Users | Backend | Entity: User | إنشاء جدول المستخدمين
Sprint 1 | Authentication & Users | Backend | Entity: UserDocument | مستندات المستخدم
Sprint 1 | Authentication & Users | Backend | Entity: UserAddress | عناوين المستخدم
Sprint 1 | Authentication & Users | Backend | Auth Register API | POST /auth/register
Sprint 1 | Authentication & Users | Backend | Verify OTP API | POST /auth/verify-otp
Sprint 1 | Authentication & Users | Backend | Refresh Token API | POST /auth/refresh-token
Sprint 1 | Authentication & Users | Backend | Current User API | GET /users/me
Sprint 1 | Authentication & Users | Backend | Update Profile API | PUT /users/me
Sprint 1 | Authentication & Users | Backend | Upload Avatar API | رفع صورة المستخدم
Sprint 1 | Authentication & Users | Backend | Roles | customer, provider, driver, admin
Sprint 1 | Authentication & Users | Backend | Authorization Policies | صلاحيات حسب الدور
Sprint 1 | Authentication & Users | Backend | Seed Admin User | إنشاء مسؤول افتراضي
Sprint 1 | Authentication & Users | Frontend | Login Page | إدخال رقم الجوال
Sprint 1 | Authentication & Users | Frontend | OTP Page | التحقق من الرمز
Sprint 1 | Authentication & Users | Frontend | Register Profile Page | إكمال بيانات المستخدم
Sprint 1 | Authentication & Users | Frontend | Auth Store | حفظ token وبيانات المستخدم
Sprint 1 | Authentication & Users | Frontend | Protected Layout | منع الدخول بدون تسجيل
Sprint 1 | Authentication & Users | Frontend | Profile Page | عرض وتعديل الملف الشخصي
Sprint 1 | Authentication & Users | UI/UX | Login | تصميم صفحة الدخول
Sprint 1 | Authentication & Users | UI/UX | OTP Verification | تصميم إدخال OTP
Sprint 1 | Authentication & Users | UI/UX | Complete Profile | بيانات الاسم والبريد
Sprint 1 | Authentication & Users | UI/UX | User Profile | الملف الشخصي
Sprint 1 | Authentication & Users | UI/UX | Empty/Error States | حالات الخطأ والتحميل
Sprint 2 | Vehicles Module | Backend | Entity: VehicleBrand | ماركات المركبات
Sprint 2 | Vehicles Module | Backend | Entity: VehicleModel | موديلات المركبات
Sprint 2 | Vehicles Module | Backend | Entity: Vehicle | مركبات المستخدم
Sprint 2 | Vehicles Module | Backend | Entity: MaintenanceHistory | سجل الصيانة
Sprint 2 | Vehicles Module | Backend | GET /brands | جلب الماركات
Sprint 2 | Vehicles Module | Backend | GET /brands/:id/models | جلب الموديلات
Sprint 2 | Vehicles Module | Backend | POST /vehicles | إضافة مركبة
Sprint 2 | Vehicles Module | Backend | GET /vehicles | قائمة مركباتي
Sprint 2 | Vehicles Module | Backend | GET /vehicles/:id | تفاصيل مركبة
Sprint 2 | Vehicles Module | Backend | PUT /vehicles/:id | تعديل مركبة
Sprint 2 | Vehicles Module | Backend | DELETE /vehicles/:id | حذف منطقي
Sprint 2 | Vehicles Module | Backend | Validation | رقم الشاصي، السنة، اللوحة
Sprint 2 | Vehicles Module | Backend | Seed Data | ماركات وموديلات أولية
Sprint 2 | Vehicles Module | Frontend | Vehicles List Page | قائمة مركباتي
Sprint 2 | Vehicles Module | Frontend | Add Vehicle Page | إضافة مركبة
Sprint 2 | Vehicles Module | Frontend | Edit Vehicle Page | تعديل مركبة
Sprint 2 | Vehicles Module | Frontend | Vehicle Details Page | تفاصيل المركبة
Sprint 2 | Vehicles Module | Frontend | Brand/Model Dropdowns | قوائم مترابطة
Sprint 2 | Vehicles Module | Frontend | Maintenance History UI | عرض سجل الصيانة
Sprint 2 | Vehicles Module | UI/UX | My Vehicles | كروت للمركبات
Sprint 2 | Vehicles Module | UI/UX | Add Vehicle Form | نموذج إضافة مركبة
Sprint 2 | Vehicles Module | UI/UX | Vehicle Details | صفحة التفاصيل
Sprint 2 | Vehicles Module | UI/UX | Maintenance Timeline | Timeline للصيانة
Sprint 3 | Services Catalog & Provider Registration | Backend | Entity: ServiceProvider | مقدم الخدمة
Sprint 3 | Services Catalog & Provider Registration | Backend | Entity: ServiceCategory | فئات الخدمات
Sprint 3 | Services Catalog & Provider Registration | Backend | Entity: ServiceSubcategory | الخدمات الفرعية
Sprint 3 | Services Catalog & Provider Registration | Backend | Entity: ProviderService | خدمات مقدم الخدمة
Sprint 3 | Services Catalog & Provider Registration | Backend | Entity: ProviderWorkingDay | أيام العمل
Sprint 3 | Services Catalog & Provider Registration | Backend | POST /providers/register | تسجيل مقدم خدمة
Sprint 3 | Services Catalog & Provider Registration | Backend | GET /services/categories | فئات الخدمات
Sprint 3 | Services Catalog & Provider Registration | Backend | GET /services/categories/:id/subcategories | الخدمات الفرعية
Sprint 3 | Services Catalog & Provider Registration | Backend | POST /provider/services | إضافة خدمة لمقدم الخدمة
Sprint 3 | Services Catalog & Provider Registration | Backend | GET /provider/services | خدماتي
Sprint 3 | Services Catalog & Provider Registration | Backend | PUT /provider/services/:id | تعديل خدمة
Sprint 3 | Services Catalog & Provider Registration | Backend | Provider KYC Status | pending, approved, rejected
Sprint 3 | Services Catalog & Provider Registration | Backend | Upload Documents | سجل تجاري، ضريبة، هوية
Sprint 3 | Services Catalog & Provider Registration | Backend | Admin Approve Provider API | موافقة المسؤول
Sprint 3 | Services Catalog & Provider Registration | Frontend | Provider Register Page | تسجيل ورشة / مقدم خدمة
Sprint 3 | Services Catalog & Provider Registration | Frontend | Provider Services Page | خدمات مقدم الخدمة
Sprint 3 | Services Catalog & Provider Registration | Frontend | Add Provider Service Form | إضافة خدمة
Sprint 3 | Services Catalog & Provider Registration | Frontend | Categories Page | عرض الفئات
Sprint 3 | Services Catalog & Provider Registration | Frontend | Provider Pending Page | حالة انتظار الموافقة
Sprint 3 | Services Catalog & Provider Registration | Frontend | Admin Providers Review Page | مراجعة مقدمي الخدمة
Sprint 3 | Services Catalog & Provider Registration | UI/UX | Service Categories | Grid للفئات
Sprint 3 | Services Catalog & Provider Registration | UI/UX | Provider Registration | Stepper للتسجيل
Sprint 3 | Services Catalog & Provider Registration | UI/UX | Provider Services | جدول الخدمات
Sprint 3 | Services Catalog & Provider Registration | UI/UX | KYC Upload | رفع مستندات
Sprint 3 | Services Catalog & Provider Registration | UI/UX | Admin Provider Approval | شاشة مراجعة
Sprint 4 | Discover Nearby Services | Backend | GET /services/nearby | البحث عن الخدمات القريبة
Sprint 4 | Discover Nearby Services | Backend | Location Query | استخدام lat/lng/radius
Sprint 4 | Discover Nearby Services | Backend | Filter by Category | فئة الخدمة
Sprint 4 | Discover Nearby Services | Backend | Filter by Rating | التقييم
Sprint 4 | Discover Nearby Services | Backend | Filter by Price | السعر
Sprint 4 | Discover Nearby Services | Backend | Filter by Availability | متاح الآن
Sprint 4 | Discover Nearby Services | Backend | Distance Calculation | حساب المسافة
Sprint 4 | Discover Nearby Services | Backend | Provider Details API | تفاصيل مقدم الخدمة
Sprint 4 | Discover Nearby Services | Backend | Favorites Entity | المفضلة
Sprint 4 | Discover Nearby Services | Backend | Add/Remove Favorite API | إضافة/إزالة مفضلة
Sprint 4 | Discover Nearby Services | Frontend | Nearby Services Page | صفحة البحث
Sprint 4 | Discover Nearby Services | Frontend | Map/List Toggle | عرض خريطة وقائمة
Sprint 4 | Discover Nearby Services | Frontend | Filters UI | فلترة السعر والتقييم
Sprint 4 | Discover Nearby Services | Frontend | Provider Card | كرت مقدم الخدمة
Sprint 4 | Discover Nearby Services | Frontend | Provider Details Page | تفاصيل مقدم الخدمة
Sprint 4 | Discover Nearby Services | Frontend | Favorite Button | المفضلة
Sprint 4 | Discover Nearby Services | UI/UX | Search Services | بحث وفلترة
Sprint 4 | Discover Nearby Services | UI/UX | Map View | خريطة
Sprint 4 | Discover Nearby Services | UI/UX | Provider Details | معلومات مقدم الخدمة
Sprint 4 | Discover Nearby Services | UI/UX | Provider Reviews Section | التقييمات
Sprint 4 | Discover Nearby Services | UI/UX | Empty Search State | لا توجد نتائج
Sprint 5 | Orders: Create Service Request | Backend | Entity: Order | الطلب
Sprint 5 | Orders: Create Service Request | Backend | Entity: OrderLocation | موقع الطلب
Sprint 5 | Orders: Create Service Request | Backend | Entity: OrderPhoto | صور الطلب
Sprint 5 | Orders: Create Service Request | Backend | Entity: OrderTracking | تتبع الحالة
Sprint 5 | Orders: Create Service Request | Backend | POST /orders | إنشاء طلب
Sprint 5 | Orders: Create Service Request | Backend | GET /orders | قائمة الطلبات
Sprint 5 | Orders: Create Service Request | Backend | GET /orders/:id | تفاصيل الطلب
Sprint 5 | Orders: Create Service Request | Backend | POST /orders/:id/cancel | إلغاء الطلب
Sprint 5 | Orders: Create Service Request | Backend | Upload Order Photos | رفع صور المشكلة
Sprint 5 | Orders: Create Service Request | Backend | Order Number Generator | ORD-2026-XXXX
Sprint 5 | Orders: Create Service Request | Backend | Initial Status Flow | created → searching
Sprint 5 | Orders: Create Service Request | Backend | Notify Nearby Providers | إشعار مقدمي الخدمة
Sprint 5 | Orders: Create Service Request | Frontend | Create Order Page | إنشاء طلب
Sprint 5 | Orders: Create Service Request | Frontend | Select Vehicle Step | اختيار المركبة
Sprint 5 | Orders: Create Service Request | Frontend | Select Service Step | اختيار الخدمة
Sprint 5 | Orders: Create Service Request | Frontend | Location Step | تحديد الموقع
Sprint 5 | Orders: Create Service Request | Frontend | Upload Photos Step | رفع صور
Sprint 5 | Orders: Create Service Request | Frontend | Order Summary Step | مراجعة الطلب
Sprint 5 | Orders: Create Service Request | Frontend | My Orders Page | قائمة طلباتي
Sprint 5 | Orders: Create Service Request | Frontend | Order Details Page | تفاصيل الطلب
Sprint 5 | Orders: Create Service Request | UI/UX | Create Order Wizard | خطوات إنشاء الطلب
Sprint 5 | Orders: Create Service Request | UI/UX | Select Vehicle | اختيار المركبة
Sprint 5 | Orders: Create Service Request | UI/UX | Select Service | اختيار الخدمة
Sprint 5 | Orders: Create Service Request | UI/UX | Location Picker | تحديد الموقع
Sprint 5 | Orders: Create Service Request | UI/UX | Upload Damage/Problem Photos | رفع الصور
Sprint 5 | Orders: Create Service Request | UI/UX | Order Status Timeline | حالة الطلب
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | Entity: OrderQuote | عرض السعر
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | GET /provider/orders | طلبات متاحة للمقدم
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | GET /provider/orders/:id | تفاصيل الطلب
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | POST /provider/orders/:id/quote | إرسال عرض سعر
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | GET /orders/:id/quotes | عروض الطلب
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | POST /orders/:id/accept-quote | قبول عرض
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | Order Status Logic | searching → quoted → accepted
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | Quote Validation | لا يسمح بعرضين من نفس المقدم لنفس الطلب
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | Expiry Logic | انتهاء صلاحية العرض
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Backend | Assignment Creation | إنشاء تخصيص للطلب بعد القبول
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Frontend | Provider Orders Page | الطلبات الجديدة
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Frontend | Provider Order Details | تفاصيل الطلب للمقدم
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Frontend | Send Quote Modal | إرسال عرض سعر
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Frontend | Customer Quotes Page | عروض الأسعار
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Frontend | Compare Quotes UI | مقارنة العروض
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | Frontend | Accept Quote Action | قبول العرض
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | UI/UX | Provider Request Details | تفاصيل طلب وارد
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | UI/UX | Quote Form | السعر، المدة، التفاصيل
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | UI/UX | Customer Quotes Compare | مقارنة العروض
Sprint 6 | Quotes: Provider Send Offer / Customer Accept | UI/UX | Accept Confirmation | تأكيد قبول العرض
Sprint 7 | Order Execution & Status Tracking | Backend | Entity: OrderAssignment | تخصيص الطلب
Sprint 7 | Order Execution & Status Tracking | Backend | POST /provider/orders/:id/update-status | تحديث حالة الطلب
Sprint 7 | Order Execution & Status Tracking | Backend | Order Status Flow | accepted → in_progress → completed
Sprint 7 | Order Execution & Status Tracking | Backend | OrderTracking Records | حفظ سجل الحالات
Sprint 7 | Order Execution & Status Tracking | Backend | Upload Before/After Photos | صور قبل وبعد
Sprint 7 | Order Execution & Status Tracking | Backend | SignalR Hub Basic | تحديث الحالة لحظيًا
Sprint 7 | Order Execution & Status Tracking | Backend | GET /orders/:id/tracking | سجل التتبع
Sprint 7 | Order Execution & Status Tracking | Backend | Business Rules | لا يمكن إكمال طلب غير مقبول
Sprint 7 | Order Execution & Status Tracking | Backend | Provider Permission | مقدم الخدمة يرى طلباته فقط
Sprint 7 | Order Execution & Status Tracking | Frontend | Provider Active Orders | الطلبات النشطة
Sprint 7 | Order Execution & Status Tracking | Frontend | Update Status Buttons | تغيير الحالة
Sprint 7 | Order Execution & Status Tracking | Frontend | Upload Before/After Photos | رفع صور الخدمة
Sprint 7 | Order Execution & Status Tracking | Frontend | Customer Live Status | عرض حالة الطلب
Sprint 7 | Order Execution & Status Tracking | Frontend | Status Timeline | Timeline
Sprint 7 | Order Execution & Status Tracking | Frontend | Real-time Updates | SignalR Client
Sprint 7 | Order Execution & Status Tracking | UI/UX | Active Order Provider | شاشة تنفيذ الطلب
Sprint 7 | Order Execution & Status Tracking | UI/UX | Customer Order Tracking | تتبع العميل
Sprint 7 | Order Execution & Status Tracking | UI/UX | Status Timeline | created, quoted, accepted, in_progress, completed
Sprint 7 | Order Execution & Status Tracking | UI/UX | Photo Before/After Gallery | معرض الصور
Sprint 8 | Payments & Wallet Basic | Backend | Entity: Payment | المدفوعات
Sprint 8 | Payments & Wallet Basic | Backend | Entity: WalletTransaction | معاملات المحفظة
Sprint 8 | Payments & Wallet Basic | Backend | Entity: WithdrawalRequest | طلبات السحب
Sprint 8 | Payments & Wallet Basic | Backend | GET /users/me/wallet | رصيد المحفظة
Sprint 8 | Payments & Wallet Basic | Backend | POST /payments/intent | إنشاء عملية دفع
Sprint 8 | Payments & Wallet Basic | Backend | POST /payments/confirm | تأكيد الدفع
Sprint 8 | Payments & Wallet Basic | Backend | POST /payments/wallet-topup | شحن المحفظة
Sprint 8 | Payments & Wallet Basic | Backend | Payment Status Flow | pending, held, captured, failed
Sprint 8 | Payments & Wallet Basic | Backend | Wallet Debit/Credit Logic | خصم وإضافة الرصيد
Sprint 8 | Payments & Wallet Basic | Backend | Provider Commission Logic | عمولة المنصة
Sprint 8 | Payments & Wallet Basic | Backend | Invoice Placeholder | توليد بيانات فاتورة بسيطة
Sprint 8 | Payments & Wallet Basic | Backend | Webhook Endpoint | نقطة استقبال من بوابة الدفع
Sprint 8 | Payments & Wallet Basic | Frontend | Wallet Page | المحفظة
Sprint 8 | Payments & Wallet Basic | Frontend | Payment Page | الدفع
Sprint 8 | Payments & Wallet Basic | Frontend | Wallet Topup Page | شحن المحفظة
Sprint 8 | Payments & Wallet Basic | Frontend | Payment Status UI | نجاح / فشل
Sprint 8 | Payments & Wallet Basic | Frontend | Order Payment Summary | ملخص الدفع
Sprint 8 | Payments & Wallet Basic | Frontend | Provider Earnings Page | أرباح مقدم الخدمة
Sprint 8 | Payments & Wallet Basic | UI/UX | Wallet | الرصيد والمعاملات
Sprint 8 | Payments & Wallet Basic | UI/UX | Checkout | طرق الدفع
Sprint 8 | Payments & Wallet Basic | UI/UX | Payment Result | نجاح أو فشل
Sprint 8 | Payments & Wallet Basic | UI/UX | Provider Earnings | أرباح مقدم الخدمة
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | Entity: Review | التقييم
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | Entity: Notification | الإشعارات
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | Entity: ChatMessage | المحادثة
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | POST /orders/:id/rate | تقييم الطلب
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | GET /provider/reviews | تقييمات مقدم الخدمة
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | Rating Aggregation | تحديث تقييم مقدم الخدمة
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | GET /users/me/notifications | إشعاراتي
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | Mark Notification Read | تحديد كمقروء
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | SignalR Chat Hub | محادثة أساسية
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | GET /orders/:id/messages | رسائل الطلب
Sprint 9 | Reviews, Notifications, Chat Basic | Backend | POST /orders/:id/messages | إرسال رسالة
Sprint 9 | Reviews, Notifications, Chat Basic | Frontend | Rating Modal | تقييم الخدمة
Sprint 9 | Reviews, Notifications, Chat Basic | Frontend | Reviews Section | عرض التقييمات
Sprint 9 | Reviews, Notifications, Chat Basic | Frontend | Notifications Center | مركز الإشعارات
Sprint 9 | Reviews, Notifications, Chat Basic | Frontend | Notification Badge | عدد غير المقروء
Sprint 9 | Reviews, Notifications, Chat Basic | Frontend | Order Chat Page | محادثة الطلب
Sprint 9 | Reviews, Notifications, Chat Basic | Frontend | Chat Component | إرسال واستقبال رسائل
Sprint 9 | Reviews, Notifications, Chat Basic | UI/UX | Rate Order | نجوم وتعليق
Sprint 9 | Reviews, Notifications, Chat Basic | UI/UX | Notifications | قائمة الإشعارات
Sprint 9 | Reviews, Notifications, Chat Basic | UI/UX | Chat | واجهة محادثة
Sprint 9 | Reviews, Notifications, Chat Basic | UI/UX | Review List | عرض التقييمات
Sprint 10 | Admin Dashboard MVP | Backend | Entity: AdminLog | سجل إجراءات المسؤول
Sprint 10 | Admin Dashboard MVP | Backend | GET /admin/dashboard | مؤشرات عامة
Sprint 10 | Admin Dashboard MVP | Backend | GET /admin/users | قائمة المستخدمين
Sprint 10 | Admin Dashboard MVP | Backend | POST /admin/users/:id/status | تفعيل/تعليق مستخدم
Sprint 10 | Admin Dashboard MVP | Backend | GET /admin/providers | مقدمو الخدمة
Sprint 10 | Admin Dashboard MVP | Backend | POST /admin/providers/:id/approve | اعتماد مقدم خدمة
Sprint 10 | Admin Dashboard MVP | Backend | POST /admin/providers/:id/suspend | تعليق مقدم خدمة
Sprint 10 | Admin Dashboard MVP | Backend | GET /admin/orders | كل الطلبات
Sprint 10 | Admin Dashboard MVP | Backend | GET /admin/orders/:id | تفاصيل طلب
Sprint 10 | Admin Dashboard MVP | Backend | GET /admin/financials | ملخص مالي
Sprint 10 | Admin Dashboard MVP | Backend | Admin Audit Logs | تسجيل قرارات المسؤول
Sprint 10 | Admin Dashboard MVP | Frontend | Admin Layout | Sidebar + Topbar
Sprint 10 | Admin Dashboard MVP | Frontend | Dashboard Page | مؤشرات
Sprint 10 | Admin Dashboard MVP | Frontend | Users Management Page | المستخدمون
Sprint 10 | Admin Dashboard MVP | Frontend | Providers Management Page | مقدمو الخدمة
Sprint 10 | Admin Dashboard MVP | Frontend | Orders Management Page | الطلبات
Sprint 10 | Admin Dashboard MVP | Frontend | Financials Page | المالية
Sprint 10 | Admin Dashboard MVP | Frontend | Provider Approval Page | مراجعة المستندات
Sprint 10 | Admin Dashboard MVP | UI/UX | Admin Dashboard | Cards + Charts
Sprint 10 | Admin Dashboard MVP | UI/UX | Users Table | جدول المستخدمين
Sprint 10 | Admin Dashboard MVP | UI/UX | Providers Review | مراجعة واعتماد
Sprint 10 | Admin Dashboard MVP | UI/UX | Orders Table | متابعة الطلبات
Sprint 10 | Admin Dashboard MVP | UI/UX | Financial Summary | ملخص مالي
Sprint 11 | Hardening, Security, Testing | Backend | Unit Tests | اختبارات Services
Sprint 11 | Hardening, Security, Testing | Backend | Integration Tests | API Tests
Sprint 11 | Hardening, Security, Testing | Backend | Validation Layer | FluentValidation
Sprint 11 | Hardening, Security, Testing | Backend | Rate Limiting | خصوصًا Auth
Sprint 11 | Hardening, Security, Testing | Backend | File Upload Security | نوع وحجم الملف
Sprint 11 | Hardening, Security, Testing | Backend | Permission Review | مراجعة الصلاحيات
Sprint 11 | Hardening, Security, Testing | Backend | Query Optimization | تحسين الاستعلامات
Sprint 11 | Hardening, Security, Testing | Backend | Indexes | فهارس مهمة
Sprint 11 | Hardening, Security, Testing | Backend | Error Handling Review | أخطاء موحدة
Sprint 11 | Hardening, Security, Testing | Backend | API Versioning | /api/v1
Sprint 11 | Hardening, Security, Testing | Backend | Health Checks | DB, Redis, Storage
Sprint 11 | Hardening, Security, Testing | Backend | Background Jobs | Hangfire/Quartz للمهام الدورية
Sprint 11 | Hardening, Security, Testing | Frontend | Form Validation | Zod / React Hook Form
Sprint 11 | Hardening, Security, Testing | Frontend | Error Boundaries | معالجة أخطاء React
Sprint 11 | Hardening, Security, Testing | Frontend | Loading States | حالات تحميل
Sprint 11 | Hardening, Security, Testing | Frontend | Empty States | حالات فارغة
Sprint 11 | Hardening, Security, Testing | Frontend | Responsive Review | تجاوب الشاشات
Sprint 11 | Hardening, Security, Testing | Frontend | API Error Handling | عرض رسائل API
Sprint 11 | Hardening, Security, Testing | Frontend | Role-based UI | إخفاء حسب الدور
Sprint 11 | Hardening, Security, Testing | UI/UX | Usability Review | مراجعة تجربة المستخدم
Sprint 11 | Hardening, Security, Testing | UI/UX | Responsive Audit | موبايل وتابلت
Sprint 11 | Hardening, Security, Testing | UI/UX | Design Consistency | توحيد المكونات
Sprint 11 | Hardening, Security, Testing | UI/UX | Arabic RTL Review | مراجعة RTL
Sprint 11 | Hardening, Security, Testing | UI/UX | Error Messages | صياغة رسائل واضحة
Sprint 11 | Hardening, Security, Testing | QA | Test Plan | خطة اختبار
Sprint 11 | Hardening, Security, Testing | QA | Test Cases | حالات اختبار
Sprint 11 | Hardening, Security, Testing | QA | Regression Testing | اختبار شامل
Sprint 11 | Hardening, Security, Testing | QA | Security Checklist | قائمة أمنية
Sprint 11 | Hardening, Security, Testing | QA | API Testing | Postman Collection
Sprint 11 | Hardening, Security, Testing | QA | Bug Report | تقارير العيوب
Sprint 12 | Deployment & UAT | Backend | Docker Build | بناء Images
Sprint 12 | Deployment & UAT | Backend | Staging Environment | تجهيز البيئة
Sprint 12 | Deployment & UAT | Backend | Migration Deployment | تطبيق migrations
Sprint 12 | Deployment & UAT | Backend | Seed Production-like Data | بيانات تجريبية
Sprint 12 | Deployment & UAT | Backend | Configure Storage | MinIO/S3
Sprint 12 | Deployment & UAT | Backend | Configure Redis | Redis
Sprint 12 | Deployment & UAT | Backend | Configure SMTP/SMS | مزود الرسائل
Sprint 12 | Deployment & UAT | Backend | CI/CD Pipeline | GitHub Actions/GitLab CI
Sprint 12 | Deployment & UAT | Backend | Monitoring | Logs + Health Checks
Sprint 12 | Deployment & UAT | Backend | Backup Strategy | نسخ احتياطي DB
Sprint 12 | Deployment & UAT | Frontend | Build React App | Production Build
Sprint 12 | Deployment & UAT | Frontend | Environment Config | API URLs
Sprint 12 | Deployment & UAT | Frontend | Deploy Admin Panel | نشر لوحة الإدارة
Sprint 12 | Deployment & UAT | Frontend | Deploy Customer/Provider Web | حسب النطاق
Sprint 12 | Deployment & UAT | Frontend | Fix UAT Bugs | إصلاح ملاحظات المستخدمين
Sprint 12 | Deployment & UAT | UI/UX | UAT Observation | مراقبة تجربة المستخدم
Sprint 12 | Deployment & UAT | UI/UX | Final UI Adjustments | تحسينات نهائية
Sprint 12 | Deployment & UAT | UI/UX | Content Review | النصوص العربية
Sprint 12 | Deployment & UAT | UI/UX | Production Assets | أيقونات وصور نهائية

## وحدات الباكند
الوحدة | الكيانات | APIs | مهام المطور
Auth Module | User, RefreshToken, UserDocument, UserAddress | POST /api/v1/auth/register, POST /api/v1/auth/verify-otp, POST /api/v1/auth/refresh-token, POST /api/v1/auth/logout, GET /api/v1/users/me, PUT /api/v1/users/me | JWT Authentication, Refresh Token, OTP Service, Role-based Authorization, CurrentUserService, Password/OTP policy, User status validation
Vehicle Module | VehicleBrand, VehicleModel, Vehicle, VehicleMaintenanceHistory | GET /api/v1/brands, GET /api/v1/brands/{id}/models, GET /api/v1/vehicles, POST /api/v1/vehicles, GET /api/v1/vehicles/{id}, PUT /api/v1/vehicles/{id}, DELETE /api/v1/vehicles/{id}, GET /api/v1/vehicles/{id}/maintenance-history | CRUD vehicles, Validate ownership, VIN uniqueness, Soft delete, Vehicle lookup data
Provider Module | ServiceProvider, ProviderService, ProviderWorkingDay, ServiceCategory, ServiceSubcategory | POST /api/v1/providers/register, GET /api/v1/provider/profile, PUT /api/v1/provider/profile, GET /api/v1/provider/services, POST /api/v1/provider/services, PUT /api/v1/provider/services/{id}, GET /api/v1/services/categories, GET /api/v1/services/categories/{id}/subcategories, GET /api/v1/services/nearby | Provider registration, Provider approval status, Location filtering, Services pricing, Provider availability, Provider dashboard
Orders Module | Order, OrderLocation, OrderQuote, OrderAssignment, OrderTracking, OrderPhoto | POST /api/v1/orders, GET /api/v1/orders, GET /api/v1/orders/{id}, POST /api/v1/orders/{id}/cancel, GET /api/v1/orders/{id}/quotes, POST /api/v1/orders/{id}/accept-quote, GET /api/v1/orders/{id}/tracking, GET /api/v1/provider/orders, GET /api/v1/provider/orders/{id}, POST /api/v1/provider/orders/{id}/quote, POST /api/v1/provider/orders/{id}/update-status | Order state machine, Create order, Notify providers, Quote lifecycle, Accept quote, Assignment, Status tracking, Upload order photos
Payment & Wallet | Payment, WalletTransaction, WithdrawalRequest | GET /api/v1/users/me/wallet, POST /api/v1/payments/intent, POST /api/v1/payments/confirm, POST /api/v1/payments/wallet-topup, POST /api/v1/payments/webhook, GET /api/v1/provider/earnings | Payment intent, Wallet balance, Debit/credit transaction, Commission calculation, Payment webhook, Refund placeholder
Notification & Chat | Notification, ChatMessage | GET /api/v1/users/me/notifications, POST /api/v1/notifications/{id}/read, GET /api/v1/orders/{id}/messages, POST /api/v1/orders/{id}/messages, /ws/orders/{id}/tracking, /ws/chat/{orderId} | SignalR hub, Notification service, Store notifications, Chat per order, Broadcast status updates
Admin Module | AdminLog, Dispute (لاحقًا), PromoCode (لاحقًا) | GET /api/v1/admin/dashboard, GET /api/v1/admin/users, POST /api/v1/admin/users/{id}/status, GET /api/v1/admin/providers, POST /api/v1/admin/providers/{id}/approve, POST /api/v1/admin/providers/{id}/suspend, GET /api/v1/admin/orders, GET /api/v1/admin/financials | Admin authorization, Dashboard counts, User management, Provider approval, Order monitoring, Audit logging

## صفحات الواجهة
البوابة | الصفحة | المسار (Route)
Customer Portal | Login | /login
Customer Portal | OTP | /verify-otp
Customer Portal | Dashboard | /app/dashboard
Customer Portal | My Vehicles | /app/vehicles
Customer Portal | Add Vehicle | /app/vehicles/create
Customer Portal | Services | /app/services
Customer Portal | Provider Details | /app/providers/:id
Customer Portal | Create Order | /app/orders/create
Customer Portal | My Orders | /app/orders
Customer Portal | Order Details | /app/orders/:id
Customer Portal | Quotes | /app/orders/:id/quotes
Customer Portal | Tracking | /app/orders/:id/tracking
Customer Portal | Wallet | /app/wallet
Customer Portal | Notifications | /app/notifications
Customer Portal | Chat | /app/orders/:id/chat
Provider Portal | Provider Dashboard | /provider/dashboard
Provider Portal | New Requests | /provider/requests
Provider Portal | Active Orders | /provider/orders/active
Provider Portal | Order Details | /provider/orders/:id
Provider Portal | Send Quote | Modal
Provider Portal | Services | /provider/services
Provider Portal | Earnings | /provider/earnings
Provider Portal | Profile/KYC | /provider/profile
Admin Portal | Admin Dashboard | /admin/dashboard
Admin Portal | Users | /admin/users
Admin Portal | Providers | /admin/providers
Admin Portal | Provider Review | /admin/providers/:id
Admin Portal | Orders | /admin/orders
Admin Portal | Order Details | /admin/orders/:id
Admin Portal | Financials | /admin/financials
Admin Portal | Settings | /admin/settings

## خطة UI UX
السبرنت | الشاشة | الوصف | المكونات المستخدمة
Sprint 0 | Design system + user flows | تحليل المستخدمين وإعداد Design System وWireframes | Colors, Typography, Buttons, Inputs, Layout grid, RTL rules
Sprint 1 | Auth screens | Login, OTP, Complete Profile, User Profile | Button, Input, Card
Sprint 2 | Vehicles screens | My Vehicles, Add Vehicle, Vehicle Details, Maintenance Timeline | Card, Table, Timeline, Form, Select
Sprint 3 | Provider registration + services | Service Categories, Provider Registration, Provider Services, KYC Upload | Stepper, Grid, Table, Upload Box
Sprint 4 | Services discovery + map/list | Search Services, Map View, Provider Details, Provider Reviews | Map Picker, Card, Badge, Modal
Sprint 5 | Create order wizard | Create Order Wizard, Select Vehicle, Select Service, Location Picker, Upload Photos | Stepper, Select, Map Picker, Upload Box, Timeline
Sprint 6 | Quotes compare + provider quote | Provider Request Details, Quote Form, Customer Quotes Compare, Accept Confirmation | Modal, Table, Card, Button
Sprint 7 | Tracking + status timeline | Active Order Provider, Customer Order Tracking, Status Timeline, Photo Gallery | Timeline, Badge, Upload Box, Card
Sprint 8 | Wallet + payment | Wallet, Checkout, Payment Result, Provider Earnings | Card, Table, Button, Badge
Sprint 9 | Reviews + notifications + chat | Rate Order, Notifications, Chat, Review List | Rating Stars, Notification Item, Chat Component
Sprint 10 | Admin dashboard | Admin Dashboard, Users Table, Providers Review, Orders Table, Financial Summary | Table, Card, Chart, Badge
Sprint 11 | Responsive + usability audit | Usability Review, Responsive Audit, Design Consistency, Arabic RTL Review | All Components
Sprint 12 | UAT improvements | UAT Observation, Final UI Adjustments, Content Review, Production Assets | All Components

## حالات الطلب
الحالة | الوصف | قواعد العمل
created | عند إنشاء الطلب | العميل ينشئ الطلب
searching | بعد إرسال الطلب لمقدمي الخدمة | يتم إخطار مقدمي الخدمة القريبين
quoted | عند وجود عرض سعر واحد على الأقل | العميل يرى قائمة العروض
accepted | عند قبول العميل لعرض | يتم إنشاء تخصيص للطلب
in_progress | عند بدء مقدم الخدمة | مقدم الخدمة يبدأ العمل
completed | عند انتهاء الخدمة | الطلب مكتمل ويمكن التقييم
cancelled | إذا ألغى العميل أو النظام | لا يمكن إلغاء طلب في حالة متقدمة
disputed | إذا فتح العميل نزاعًا | يتم تأجيلها للمرحلة الثانية

## مهام المطورين
الدور | Epic | المهمة
Backend | Epic 1 — Foundation | Create solution architecture
Backend | Epic 1 — Foundation | Setup EF Core
Backend | Epic 1 — Foundation | Setup Sql Server
Backend | Epic 1 — Foundation | Setup Identity/Auth
Backend | Epic 1 — Foundation | Setup JWT
Backend | Epic 1 — Foundation | Setup Swagger
Backend | Epic 1 — Foundation | Setup Serilog
Backend | Epic 1 — Foundation | Setup Result Pattern
Backend | Epic 1 — Foundation | Setup Pagination
Backend | Epic 1 — Foundation | Setup Global Exception Middleware
Backend | Epic 1 — Foundation | Setup File Storage Service
Backend | Epic 1 — Foundation | Setup Docker Compose
Backend | Epic 2 — Auth & Users | Create User entity
Backend | Epic 2 — Auth & Users | Create UserDocument entity
Backend | Epic 2 — Auth & Users | Create UserAddress entity
Backend | Epic 2 — Auth & Users | Register API
Backend | Epic 2 — Auth & Users | Verify OTP API
Backend | Epic 2 — Auth & Users | Refresh token API
Backend | Epic 2 — Auth & Users | Current user API
Backend | Epic 2 — Auth & Users | Update profile API
Backend | Epic 2 — Auth & Users | Upload avatar API
Backend | Epic 2 — Auth & Users | User status middleware
Backend | Epic 2 — Auth & Users | RBAC policies
Backend | Epic 3 — Vehicles | Create VehicleBrand entity
Backend | Epic 3 — Vehicles | Create VehicleModel entity
Backend | Epic 3 — Vehicles | Create Vehicle entity
Backend | Epic 3 — Vehicles | Create maintenance history entity
Backend | Epic 3 — Vehicles | Create vehicles CRUD
Backend | Epic 3 — Vehicles | Add brand/model APIs
Backend | Epic 3 — Vehicles | Add validation
Backend | Epic 3 — Vehicles | Add ownership authorization
Backend | Epic 3 — Vehicles | Add seed data
Backend | Epic 4 — Providers & Services | Create provider entity
Backend | Epic 4 — Providers & Services | Create service category entity
Backend | Epic 4 — Providers & Services | Create subcategory entity
Backend | Epic 4 — Providers & Services | Create provider service entity
Backend | Epic 4 — Providers & Services | Register provider API
Backend | Epic 4 — Providers & Services | Upload KYC documents
Backend | Epic 4 — Providers & Services | Admin approve provider
Backend | Epic 4 — Providers & Services | Add service APIs
Backend | Epic 4 — Providers & Services | Nearby services API
Backend | Epic 4 — Providers & Services | Provider dashboard API
Backend | Epic 5 — Orders | Create order entity
Backend | Epic 5 — Orders | Create order location entity
Backend | Epic 5 — Orders | Create order photos entity
Backend | Epic 5 — Orders | Create order tracking entity
Backend | Epic 5 — Orders | Create order assignment entity
Backend | Epic 5 — Orders | Create order number generator
Backend | Epic 5 — Orders | Create order API
Backend | Epic 5 — Orders | Cancel order API
Backend | Epic 5 — Orders | Provider available orders API
Backend | Epic 5 — Orders | Order details API
Backend | Epic 6 — Quotes | Create order quote entity
Backend | Epic 6 — Quotes | Send quote API
Backend | Epic 6 — Quotes | Get quotes API
Backend | Epic 6 — Quotes | Accept quote API
Backend | Epic 6 — Quotes | Quote expiry job
Backend | Epic 6 — Quotes | Update order status on quote
Backend | Epic 6 — Quotes | Create assignment after accept
Backend | Epic 7 — Execution | Provider update status API
Backend | Epic 7 — Execution | Create tracking records
Backend | Epic 7 — Execution | SignalR order tracking
Backend | Epic 7 — Execution | Upload before/after photos
Backend | Epic 7 — Execution | Validate status transitions
Backend | Epic 7 — Execution | Customer tracking API
Backend | Epic 8 — Payments | Create payment entity
Backend | Epic 8 — Payments | Create wallet transaction entity
Backend | Epic 8 — Payments | Wallet balance API
Backend | Epic 8 — Payments | Payment intent API
Backend | Epic 8 — Payments | Confirm payment API
Backend | Epic 8 — Payments | Webhook API
Backend | Epic 8 — Payments | Wallet top-up API
Backend | Epic 8 — Payments | Provider earnings API
Backend | Epic 8 — Payments | Commission calculation
Backend | Epic 9 — Reviews & Notifications | Create review entity
Backend | Epic 9 — Reviews & Notifications | Rate order API
Backend | Epic 9 — Reviews & Notifications | Update provider rating
Backend | Epic 9 — Reviews & Notifications | Create notification entity
Backend | Epic 9 — Reviews & Notifications | Get notifications API
Backend | Epic 9 — Reviews & Notifications | Mark as read API
Backend | Epic 9 — Reviews & Notifications | Notification service
Backend | Epic 9 — Reviews & Notifications | Push notification placeholder
Backend | Epic 10 — Admin | Admin dashboard API
Backend | Epic 10 — Admin | Users list API
Backend | Epic 10 — Admin | User status update API
Backend | Epic 10 — Admin | Providers list API
Backend | Epic 10 — Admin | Approve provider API
Backend | Epic 10 — Admin | Suspend provider API
Backend | Epic 10 — Admin | Orders list API
Backend | Epic 10 — Admin | Financial summary API
Backend | Epic 10 — Admin | Admin logs
Frontend | Epic 1 — App Foundation | Setup Vite React TypeScript
Frontend | Epic 1 — App Foundation | Setup Tailwind
Frontend | Epic 1 — App Foundation | Setup routing
Frontend | Epic 1 — App Foundation | Setup protected routes
Frontend | Epic 1 — App Foundation | Setup axios client
Frontend | Epic 1 — App Foundation | Setup auth store
Frontend | Epic 1 — App Foundation | Setup layout system
Frontend | Epic 1 — App Foundation | Setup form library
Frontend | Epic 1 — App Foundation | Setup toast notifications
Frontend | Epic 1 — App Foundation | Setup shared components
Frontend | Epic 2 — Auth | Login page
Frontend | Epic 2 — Auth | OTP page
Frontend | Epic 2 — Auth | Complete profile page
Frontend | Epic 2 — Auth | Logout
Frontend | Epic 2 — Auth | Auth redirect
Frontend | Epic 2 — Auth | Role-based redirect
Frontend | Epic 3 — Customer | Customer dashboard
Frontend | Epic 3 — Customer | Vehicles list
Frontend | Epic 3 — Customer | Add vehicle
Frontend | Epic 3 — Customer | Edit vehicle
Frontend | Epic 3 — Customer | Services list
Frontend | Epic 3 — Customer | Provider details
Frontend | Epic 3 — Customer | Create order wizard
Frontend | Epic 3 — Customer | My orders
Frontend | Epic 3 — Customer | Order details
Frontend | Epic 3 — Customer | Quotes compare
Frontend | Epic 3 — Customer | Tracking page
Frontend | Epic 3 — Customer | Wallet page
Frontend | Epic 3 — Customer | Notifications
Frontend | Epic 3 — Customer | Chat
Frontend | Epic 4 — Provider | Provider registration
Frontend | Epic 4 — Provider | KYC upload
Frontend | Epic 4 — Provider | Provider dashboard
Frontend | Epic 4 — Provider | New requests
Frontend | Epic 4 — Provider | Send quote
Frontend | Epic 4 — Provider | Active orders
Frontend | Epic 4 — Provider | Update order status
Frontend | Epic 4 — Provider | Provider services
Frontend | Epic 4 — Provider | Provider earnings
Frontend | Epic 4 — Provider | Provider profile
Frontend | Epic 5 — Admin | Admin dashboard
Frontend | Epic 5 — Admin | Users table
Frontend | Epic 5 — Admin | Providers table
Frontend | Epic 5 — Admin | Provider approval details
Frontend | Epic 5 — Admin | Orders table
Frontend | Epic 5 — Admin | Order details
Frontend | Epic 5 — Admin | Financials page
Frontend | Epic 5 — Admin | Admin logs page
Frontend | Epic 6 — Real-time | Setup SignalR client
Frontend | Epic 6 — Real-time | Tracking updates
Frontend | Epic 6 — Real-time | Chat messages
Frontend | Epic 6 — Real-time | Notification badge
Frontend | Epic 7 — Polish | Loading states
Frontend | Epic 7 — Polish | Error states
Frontend | Epic 7 — Polish | Empty states
Frontend | Epic 7 — Polish | Responsive design
Frontend | Epic 7 — Polish | RTL fixes
Frontend | Epic 7 — Polish | Accessibility improvements
UI/UX | Epic 1 — Research & Flow | Define personas
UI/UX | Epic 1 — Research & Flow | Define customer journey
UI/UX | Epic 1 — Research & Flow | Define provider journey
UI/UX | Epic 1 — Research & Flow | Define admin journey
UI/UX | Epic 1 — Research & Flow | Draw order lifecycle
UI/UX | Epic 1 — Research & Flow | Draw quote lifecycle
UI/UX | Epic 2 — Design System | Color palette
UI/UX | Epic 2 — Design System | Typography
UI/UX | Epic 2 — Design System | Buttons
UI/UX | Epic 2 — Design System | Forms
UI/UX | Epic 2 — Design System | Cards
UI/UX | Epic 2 — Design System | Tables
UI/UX | Epic 2 — Design System | Badges
UI/UX | Epic 2 — Design System | Icons
UI/UX | Epic 2 — Design System | Layout grid
UI/UX | Epic 2 — Design System | RTL rules
UI/UX | Epic 3 — Customer Screens | Login
UI/UX | Epic 3 — Customer Screens | OTP
UI/UX | Epic 3 — Customer Screens | Dashboard
UI/UX | Epic 3 — Customer Screens | Vehicles
UI/UX | Epic 3 — Customer Screens | Services
UI/UX | Epic 3 — Customer Screens | Provider profile
UI/UX | Epic 3 — Customer Screens | Create order
UI/UX | Epic 3 — Customer Screens | Quotes
UI/UX | Epic 3 — Customer Screens | Order tracking
UI/UX | Epic 3 — Customer Screens | Wallet
UI/UX | Epic 3 — Customer Screens | Reviews
UI/UX | Epic 3 — Customer Screens | Notifications
UI/UX | Epic 4 — Provider Screens | Provider registration
UI/UX | Epic 4 — Provider Screens | Dashboard
UI/UX | Epic 4 — Provider Screens | Requests
UI/UX | Epic 4 — Provider Screens | Quote form
UI/UX | Epic 4 — Provider Screens | Active order
UI/UX | Epic 4 — Provider Screens | Services management
UI/UX | Epic 4 — Provider Screens | Earnings
UI/UX | Epic 5 — Admin Screens | Dashboard
UI/UX | Epic 5 — Admin Screens | Users
UI/UX | Epic 5 — Admin Screens | Providers
UI/UX | Epic 5 — Admin Screens | Provider review
UI/UX | Epic 5 — Admin Screens | Orders
UI/UX | Epic 5 — Admin Screens | Financials
UI/UX | Epic 5 — Admin Screens | Settings
UI/UX | Epic 6 — Prototype | Interactive Figma prototype
UI/UX | Epic 6 — Prototype | Mobile responsive views
UI/UX | Epic 6 — Prototype | Admin web responsive views
UI/UX | Epic 6 — Prototype | Handoff to developers
UI/UX | Epic 6 — Prototype | Components naming
UI/UX | Epic 6 — Prototype | Design tokens

## Definition of Done
الفئة | المعيار
Backend | الكود مكتوب وفق Clean Architecture
Backend | يوجد DTO واضح للطلب والاستجابة
Backend | يوجد Validation
Backend | يوجد Authorization
Backend | الأخطاء موحدة
Backend | Swagger محدث
Backend | Migration مضافة
Backend | Unit/Integration test إذا كانت المهمة حرجة
Backend | لا توجد بيانات حساسة في Logs
Frontend | الشاشة مطابقة للتصميم
Frontend | تدعم RTL
Frontend | متجاوبة
Frontend | يوجد loading state
Frontend | يوجد error state
Frontend | يوجد empty state
Frontend | تم ربطها فعليًا بالـ API
Frontend | لا توجد console errors
UI/UX | التصميم مرفوع على Figma
UI/UX | المكونات موحدة
UI/UX | الحالات المختلفة موثقة
UI/UX | يوجد prototype للتدفق المهم
UI/UX | تم تسليم الـ assets للمطورين

## الأولويات
الأولوية | الميزة
Must Have | Auth
Must Have | Users
Must Have | Vehicles
Must Have | Providers
Must Have | Services
Must Have | Orders
Must Have | Quotes
Must Have | Status tracking
Must Have | Payments basic
Must Have | Reviews
Must Have | Notifications
Must Have | Admin approval
Should Have | Chat
Should Have | Wallet top-up
Should Have | Provider earnings
Should Have | File upload
Should Have | Favorites
Should Have | Basic dashboard charts
Could Have | Accident reports
Could Have | Insurance documents
Could Have | Driver live tracking
Could Have | Promo codes
Could Have | Disputes
Later | AI damage estimation
Later | OCR
Later | Insurance comparison
Later | E-commerce
Later | Elasticsearch
Later | Advanced analytics

## التقنية
الطبقة | التقنية | الاستخدام
Backend | ASP.NET Core 8 | إطار العمل الرئيسي
Backend | EF Core | ORM لقاعدة البيانات
Backend | Sql Server/Sql Server + PostGIS | قاعدة البيانات والموقع الجغرافي
Backend | Redis | التخزين المؤقت
Backend | SignalR | التحديثات اللحظية
Backend | MediatR | التواصل بين المكونات
Backend | FluentValidation | التحقق من البيانات
Backend | Serilog | تسجيل الأخطاء
Backend | JWT | المصادقة
Backend | MinIO/S3 | تخزين الملفات
Backend | Docker | الحاويات
Frontend | React | إطار الواجهة
Frontend | TypeScript | النوعية
Frontend | Vite | أداة البناء
Frontend | Tailwind CSS | التنسيق
Frontend | shadcn/ui | مكونات واجهة المستخدم
Frontend | React Hook Form | إدارة النماذج
Frontend | Zod | التحقق من النماذج
Frontend | TanStack Query | إدارة البيانات
Frontend | Zustand | إدارة الحالة
Frontend | SignalR Client | التحديثات اللحظية
Frontend | Axios | طلبات HTTP
Architecture | Clean Architecture | هيكل المشروع
Architecture | Domain Driven Modules | تنظيم الوحدات
Architecture | CQRS for complex flows | الأوامر والاستعلامات
Architecture | Modular Monolith | في البداية
Architecture | Microservices | لاحقًا عند التوسع

## خطة MVP سريعة
Sprint | النطاق
Sprint 0 | Setup + Architecture
Sprint 1 | Auth + Users
Sprint 2 | Vehicles + Services
Sprint 3 | Provider Registration + Admin Approval
Sprint 4 | Create Order
Sprint 5 | Quotes + Accept Quote
Sprint 6 | Order Execution + Tracking
Sprint 7 | Payment + Review + Admin Dashboard

## المخرجات
السبرنت | المخرجات
Sprint 0 | Repository جاهز, Backend skeleton, Frontend skeleton, Docker development environment, Design system أولي, Swagger شغال
Sprint 12 | نسخة Staging, Postman Collection, Swagger Documentation, Admin credentials, Test report, Release notes